## Bill-1
Payment Certificate
Company Name |  | Mohd Ahmad Ateekur Raheman |  |  | Invoice No. |  |  | 1
Vendor Name |  | Sahilbhai
To, Tanvi Infracon |  |  |  |  | Date - |  | 2024-02-13
Type of Work - |  | Gypsum With material Work |  |  | Bill Date |  | 2024-02-07
Type of Contract - |  | Gypsum patra punning work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | No. of Flats | Rate | Amount
1 | D- Building Gypsum Punning work |  | 100% | 2886 | Sq.ft. per Flat | 13 | 6.75 | 253246.5
2 | Basin Above Ceiling work |  | 100% | 4.5 | Sq.ft. per Flat | 13 | 55 | 3217.5
3 | D- Building Gypsum Punning work |  | 100% | 2801.45 | Sq.ft. per Flat | 13 | 6.75 | 245827.2375
| Total Bill Amount | [6 empty] | 502291.2375
| Central GST 9% | [6 empty] | -
| State GST 9% | [6 empty] | -
Debit
502291.2375
Five Lakh Two Thousand Two Hundred Ninty One Only
Advance Payment
Retention 5%
| Balance Payment to be paid | [6 empty] | 502291.2375
Approved By -

## Bill-2
Payment Certificate
Company Name |  | Mohd Ahmad Ateekur Raheman |  |  | Invoice No. |  |  | 2
Vendor Name |  | Sahilbhai
To, Tanvi Infracon |  |  |  |  | Date - |  | 2024-02-13
Type of Work - |  | Gypsum With material Work |  |  | Bill Date |  | 2024-02-13
Type of Contract - |  | Gypsum patra punning work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | No. of Flats | Rate | Amount
1 | E-Building Gypsum Punning work (12 No. Line) |  | 100% | 2801 | Sq.ft. per Flat | 10 | 6.75 | 189067.5
2 | Basin Above Ceiling work |  | 100% | 4.5 | Sq.ft. per Flat | 9 | 55 | 2227.5
3 | E- Building Gypsum Punning work (11 No. Line) |  | 100% | 2886 | Sq.ft. per Flat | 9 | 6.75 | 175324.5
| Total Bill Amount | [6 empty] | 366619.5
| Central GST 9% | [6 empty] | -
| State GST 9% | [6 empty] | -
Debit
366619.5
Three Lakh Sixty Six Thousand Six Hundred Twenty Only
Advance Payment
Retention 5%
| Balance Payment to be paid | [6 empty] | 366619.5
Approved By -

## Bill-3
Payment Certificate
Company Name |  | Mohd Ahmad Ateekur Raheman |  |  | Invoice No. |  |  | 3
Vendor Name |  | Sahilbhai
To, Tanvi Infracon |  |  |  |  | Date - |  | 2024-06-07
Type of Work - |  | Gypsum With material Work |  |  | Bill Date |  | 2024-06-05
Type of Contract - |  | Gypsum patra punning work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | No. of Flats | Rate | Amount
1 | D- Building Gypsum Ceiling Work |  | 100% | 3456 | Sq.ft. | 1 | 55 | 190080
2 | Ceiling groove work |  | 100% | 182 | R.ft. | 1 | 12 | 2184
3 | C- Building Gypsum Patra Punning work (23 Flats) |  | 100% | 2912.25 | Sq.ft. / R.ft. | 23 | 6.75 | 452126.8125
| Total Bill Amount | [6 empty] | 644390.8125
| Central GST 9% | [6 empty] | -
| State GST 9% | [6 empty] | -
Debit
644390.8125
Six lakh Fourty Four Thousand Three Hundred Ninty one Only
Advance Payment
Retention 5%
| Balance Payment to be paid | [6 empty] | 644390.8125
Approved By -

## Bill-4
Payment Certificate
Company Name |  | Gaush Mohammad Khan |  |  | Invoice No. |  |  | 4
Vendor Name |  | Sahilbhai
To, Tanvi Infracon |  |  |  |  | Date - |  | 2024-08-17
Type of Work - |  | Gypsum With material Work |  |  | Bill Date |  | 2024-08-05
Type of Contract - |  | Gypsum patra punning work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | No. of Flats | Rate | Amount
1 | E- Building Gypsum Ceiling Work (1st to 13th Floor) |  | 100% | 3456 | Sq.ft. | 1 | 55 | 190080
2 | E- Building Ceiling groove work |  | 100% | 182 | R.ft. | 1 | 12 | 2184
3 | C- Building Gypsum Patra Punning work (21 Flats) |  | 100% | 2823.6875 | Sq.ft. / R.ft. | 21 | 6.75 | 400257.7031
| Total Bill Amount | [6 empty] | 592521.7031
| Central GST 9% | [6 empty] | -
| State GST 9% | [6 empty] | -
Debit
592521.7031
Five Lakh Ninty Two Thousand Five Hundred Twenty Two Only
Advance Payment
Retention 5%
| Balance Payment to be paid | [6 empty] | 592521.7031
Approved By -

## Bill-5
Payment Certificate
Company Name |  | Gaush Mohammad Khan |  |  | Invoice No. |  |  | 5
Vendor Name |  | Sahilbhai
To, Tanvi Infracon |  |  |  |  | Date - |  | 2024-09-26
Type of Work - |  | Gypsum With material Work |  |  | Bill Date |  | 2024-09-26
Type of Contract - |  | Gypsum patra punning work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | No. of Flats | Rate | Amount
1 | B- Building Gypsum Patra Punning work (11 Flats) |  | 100% | 2801.45 | Sq.ft. | 11 | 6.75 | 208007.6625
2 | B- Building Gypsum Patra Punning work (13 Flats) |  | 100% | 2886 | R.ft. | 13 | 6.75 | 253246.5
3 | Basin area Ceiling work |  | 100% | 4.5 | Sq.ft. | 13 | 55 | 3217.5
4 | E- Building Gypsum Patra Punning work (2 Flats) |  | 100% | 2886 | R.ft. | 2 | 6.75 | 38961
5 | C- Building Gypsum Ceiling Work (1st Floor to 13th Floor) |  | 100% | 3573.375 | Sq.ft. | 1 | 55 | 196535.625
| Total Bill Amount | [6 empty] | 699968.2875
| Central GST 9% | [6 empty] | -
| State GST 9% | [6 empty] | -
Debit
699968.2875
Six Lakh Ninty Nine Thousand Nine Hundred Sixty Eight Only
Advance Payment
Retention 5%
| Balance Payment to be paid | [6 empty] | 699968.2875
Approved By -

## Bill-6
Payment Certificate
Company Name |  | Gaush Mohammad Khan |  |  | Invoice No. |  |  | 6
Vendor Name |  | Sahilbhai
To, Tanvi Infracon |  |  |  |  | Date - |  | 2024-12-28
Type of Work - |  | Gypsum With material Work |  |  | Bill Date |  | 2024-12-28
Type of Contract - |  | Gypsum patra punning work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | No. of Flats | Rate | Amount
1 | A- Building Gypsum Patra Punning work (11 Flats) |  | 100% | 2801.45 | Sq.ft. | 11 | 6.75 | 208007.6625
2 | A- Building Gypsum Patra Punning work (12 Flats) |  | 100% | 2886 | R.ft. | 12 | 6.75 | 233766
3 | Basin area Ceiling work |  | 100% | 4.5 | Sq.ft. | 12 | 55 | 2970
| Total Bill Amount | [6 empty] | 444743.6625
| Central GST 9% | [6 empty] | -
| State GST 9% | [6 empty] | -
Debit
444743.6625
Four Lakh Fourty Four Thousand Seven Hundred Fourty Four Only
Advance Payment
Retention 5%
| Balance Payment to be paid | [6 empty] | 444743.6625
Approved By -

## Bill-7
Payment Certificate
Company Name |  | Gaush Mohammad Khan |  |  | Invoice No. |  |  | 7
Vendor Name |  | Sahilbhai
To, Tanvi Infracon |  |  |  |  | Date - |  | 2025-02-14
Type of Work - |  | Gypsum With material Work |  |  | Bill Date |  | 2025-02-11
Type of Contract - |  | Gypsum patra punning work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | No. of Flats | Rate | Amount
1 | A- Building Staircase, Lift passage Ceiling 1st to 13th Floor |  | 100% | 3454 | Sq.ft. | 1 | 55 | 189970
2 | Passage Groove |  | 100% | 182 | R.ft. | 1 | 12 | 2184
3 | B- Building Staircase, Lift passage Ceiling 1st to 13th Floor |  | 100% | 3454 | Sq.ft. | 1 | 55 | 189970
4 | Passage Groove |  | 100% | 182 | Sq.ft. | 1 | 12 | 2184
5 | A and B Building Ceiling cleaning work (47 Flats) |  | 100% | 47 | Nos. | 1 | 1000 | 47000
| Total Bill Amount | [6 empty] | 431308
| Central GST 9% | [6 empty] | -
| State GST 9% | [6 empty] | -
Debit
431308
Four Lakh Thirty One Thousand Three Hundred Eight Only
Advance Payment
Retention 5%
| Balance Payment to be paid | [6 empty] | 431308
Approved By -

## Bill-8
Payment Certificate
Company Name |  | Gaush Mohammad Khan |  |  | Invoice No. |  |  | 8
Vendor Name |  | Sahilbhai
To, Tanvi Infracon |  |  |  |  | Date - |  | 2025-03-24
Type of Work - |  | Gypsum With material Work |  |  | Bill Date |  | 2025-03-24
Type of Contract - |  | Gypsum patra punning work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | No. of Flats | Rate | Amount
1 | Ground floor For Ceiling, lift and staircase (D,E,B,A,C and Ramp) |  | 100% | 5708 | Sq.ft. | 1 | 55 | 313940
2 | Total Groove 5 Building |  | 100% | 531 | R.ft. | 1 | 12 | 6372
3 | MR Board Ceiling |  | 100% | 232 | Sq.ft. | 1 | 90 | 20880
| Total Bill Amount | [6 empty] | 341192
| Central GST 9% | [6 empty] | -
| State GST 9% | [6 empty] | -
Debit
341192
Three Lakh Fourty One Thousand One Hundred Ninty Two Only
Advance Payment
Retention 5%
| Balance Payment to be paid | [6 empty] | 341192
Approved By -