## 1
Payment Certificate
Company Name |  | JND Enterprise |  |  | Invoice No.
Vendor Name |  | Gopalbhai Ram
To, Tanvi Infracon - Aranya 2 Project |  |  |  |  | Date - | 2024-10-03
Type of Work - |  | Electrical Work |  |  | Bill Date | 2024-10-03
Type of Contract - |  | With Material Electrical Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | 3 BHK. Building Slab Conduting Work A,B,D & E (15% of Entire Work) |  | 100% | 100 | Flats | 13606.5 | 1360650 | 16327.8 | 90710 | 107037.8
2 | 3 BHK. Building Slab Conduting Work C (15% of Entire Work) |  | 100% | 50 | Flats | 13987.65 | 699382.5 | 16785.18 | 93251 | 110036.18
3 | 3 BHK. Building Wall Conduting Work A,B,D & E (15% of Entire Work) |  | 100% | 100 | Flats | 13606.5 | 1360650
4 | 3 BHK. Building Wall Conduting Work C (15% of Entire Work) |  | 100% | 50 | Flats | 13987.65 | 699382.5
5 | 3 BHK. Building Slab Conduting Work A,B,D & E (15% of Entire Work) (7% Discount of Naked Flat) |  | 100% | 4 | Flats | 12654.045 | 50616.18
6 | 3 BHK. Building Slab Conduting Work C (15% of Entire Work) (7% Discount of Naked Flat) |  | 100% | 2 | Flats | 13008.5145 | 26017.029
7 | 3 BHK. Building Wall Conduting Work A,B,D & E (15% of Entire Work) (7% Discount of Naked Flat) |  | 100% | 4 | Flats | 12654.045 | 50616.18
8 | 3 BHK. Building Wall Conduting Work C (15% of Entire Work) (7% Discount of Naked Flat) |  | 100% | 2 | Flats | 13008.5145 | 26017.029
| Total Bill Amount | [5 empty] | 4273331.418
| CGST @ 9% | [5 empty] | 384599.8276 | 20163765.7308
| SGST @ 9% | [5 empty] | 384599.8276
5042531.0732
Fifty Lakh Fourty Two Thousand Five Hundred Thirty One Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 5042531.0732
TDS will be deducted as per applicable rules at your end
Approved By -

## 2
Payment Certificate
Company Name |  | JND Enterprise |  |  | Invoice No.
Vendor Name |  | Gopalbhai Ram
To, Tanvi Infracon - Aranya 2 Project |  |  |  |  | Date - | 2025-03-28
Type of Work - |  | Electrical Work |  |  | Bill Date | 2025-03-28
Type of Contract - |  | With Material Electrical Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | 3 BHK. Building Internal Wiring Work A,B,D & E (40% of Entire Work) |  | 100% | 100 | Flats | 36284 | 3628400 | 107037.8 | 11131931.2
2 | 3 BHK. Building Internal Wiring Work C (40% of Entire Work) |  | 100% | 50 | Flats | 37300.4 | 1865020 | 110036.18 | 5721881.36
3 | 3 BHK. Building Switch board fitting Work A,B,D & E (15% of Entire Work) |  | 100% | 100 | Flats | 13606.5 | 1360650
4 | 3 BHK. Building Switch board fitting Work C (15% of Entire Work) |  | 100% | 50 | Flats | 13987.65 | 699382.5
5 | 3 BHK. Building Handover Work A,B,D & E (15% of Entire Work) |  | 100% | 100 | Flats | 13606.5 | 1360650
6 | 3 BHK. Building Handover Work C (15% of Entire Work) |  | 100% | 50 | Flats | 13987.65 | 699382.5
7 | 3 BHK. Building Internal Wiring Work A,B,D & E (40% of Entire Work) (7% Discount of Naked Flat) |  | 100% | 4 | Flats | 33744.12 | 134976.48
8 | 3 BHK. Building Internal Wiring Work C (40% of Entire Work) (7% Discount of Naked Flat) |  | 100% | 2 | Flats | 34689.372 | 69378.744
9 | 3 BHK. Building Switch board fitting Work A,B,D & E (15% of Entire Work) (7% Discount of Naked Flat) |  | 100% | 4 | Flats | 12654.045 | 50616.18
10 | 3 BHK. Building Switch board fitting Work C (15% of Entire Work) (7% Discount of Naked Flat) |  | 100% | 2 | Flats | 13008.5145 | 26017.029
11 | 3 BHK. Building Handover Work A,B,D & E (15% of Entire Work) (7% Discount of Naked Flat) |  | 100% | 4 | Flats | 12654.045 | 50616.18
12 | 3 BHK. Building Handover Work C (15% of Entire Work) (7% Discount of Naked Flat) |  | 100% | 2 | Flats | 13008.5145 | 26017.029
| Total Bill Amount | [5 empty] | 9971106.642
| CGST @ 9% | [5 empty] | 897399.5978
| SGST @ 9% | [5 empty] | 897399.5978
11765905.8376
One Crore Seventeen Lakh Sixty Five Thousand Nine Hundred Six Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 11765905.8376
TDS will be deducted as per applicable rules at your end
Approved By -

## 3
Payment Certificate
Company Name |  | JND Enterprise |  |  |  | Invoice No.
Vendor Name |  | Gopalbhai Ram
To, Tanvi Infracon - Aranya 2 Project | [5 empty] | Date - | 2025-07-16
Type of Work - |  | Electrical Work |  |  |  | Bill Date | 2025-07-11
Type of Contract - |  | With Material Electrical Work
Payment Details
Sr. No. | Items |  |  | % of Work Completed | Unit | Qty. | Rate | Amount
1 | Light Point |  |  | 100% | nos | 1217 | 370 | 450290 | 107037.8 | 11131931.2
2 | Out Door Light Point | Out Door Light Point | Out Door Light Point | 100% | nos | 371 | 490 | 181790 | 110036.18 | 5721881.36
3 | Fan Point | Fen Point | Fen Point | 100% | nos | 18 | 370 | 6660
4 | Telephone Point | Telephon Point | Telephon Point | 100% | nos | 8 | 250 | 2000
5 | 6 Amp Plug Point | 6 Amp Plug Point | 6 Amp Plug Point | 100% | nos | 65 | 350 | 22750
6 | 16 Amp Plug Point | 16 Amp Plug Point | 16 Amp Plug Point | 100% | nos | 49 | 550 | 26950
7 | AC Point | AC Point | AC Point | 100% | nos | 14 | 700 | 9800
8 | 1.5 sqmm Main Line | 1.5 sqmm Main Line | 1.5 sqmm Main Line | 100% | mtr | 842 | 87 | 73254
9 | 2.5 sqmm Main Line | 2.5 sqmm Main Line | 2.5 sqmm Main Line | 100% | mtr | 275 | 115 | 31625
10 | 6 sqmm Main Line | 6 sqmm Main Line | 6 sqmm Main Line | 100% | mtr | 297 | 375 | 111375
11 | 1.5 sqmm X 3 core Copper Flexible Cable | 1.5 sqmm X 3 core Copper Flexible Cable | 1.5 sqmm X 3 core Copper Flexible Cable | 100% | mtr | 1801 | 115 | 207115
12 | 2.5 sqmm X 3 core Copper Flexible Cable | 2.5 sqmm X 3 core Copper Flexible Cable | 2.5 sqmm X 3 core Copper Flexible Cable | 100% | mtr | 845 | 125 | 105625
13 | 4 sqmm X 3 core Copper Flexible Cable | 4 sqmm X 3 core Copper Flexible Cable | 4 sqmm X 3 core Copper Flexible Cable | 100% | mtr | 499 | 130 | 64870 | 107037.8 | 11131931.2
14 | Cat-6 | Cat-6 | Cat-6 | 100% | mtr | 3571 | 60 | 214260 | 110036.18 | 5721881.36
15 | Telephone Wire Two Pair | Telephon Wire Two Pair | Telephon Wire Two Pair | 100% | mtr | 2593 | 60 | 155580
16 | Telephone Cable 10 to 20 Pair | Telephon Cable 10 to 20 Pair | Telephon Cable 10 to 20 Pair | 100% | mtr | 1035 | 100 | 103500
17 | 300 sqmm X 3.5 Core Alu. Armoud Cable | 300sqmm X 3.5 Core Alu Armoud Cable | 300sqmm X 3.5 Core Alu Armoud Cable | 100% | mtr | 515 | 60 | 30900
18 | 150 &95 sqmm X 3.5 Alu. Armoud Cable | 150&95 sqmm X 3.5 Alu Armoud Cable | 150&95 sqmm X 3.5 Alu Armoud Cable | 100% | mtr | 492 | 40 | 19680 | 107037.8 | 11131931.2
19 | 10 to 20 Amp DP MCB | 10 to 20 Amp DP MCB | 10 to 20 Amp DP MCB | 100% | nos | 64 | 550 | 35200 | 110036.18 | 5721881.36
20 | 40 to 63 Amp FP MCB | 40 to 63 Amp FP MCB | 40 to 63 Amp FP MCB | 100% | nos | 18 | 1800 | 32400
21 | 100 AMP MCCB With Enclosure | 100 AMP MCCB With Enclosure | 100 AMP MCCB With Enclosure | 100% | nos | 1 | 11900 | 11900
22 | 250 AMP MCCB With Enclosure | 250 AMP MCCB With Enclosure | 250 AMP MCCB With Enclosure | 100% | nos | 1 | 18000 | 18000
23 | 400 AMP MCCB With Enclosure & ELR Switch | 400 AMP MCCB With Enclosure & ELR Switch | 400 AMP MCCB With Enclosure & ELR Switch | 100% | nos | 1 | 48000 | 48000
24 | 630 AMP MCCB With Enclosure | 630 AMP MCCB With Enclosure | 630 AMP MCCB With Enclosure | 100% | nos | 5 | 65000 | 325000
25 | 18 Way DB | 18 Way DB | 18 Way DB | 100% | nos | 1 | 3000 | 3000
26 | 12 Way DB | 12 Way DB | 12 Way DB | 100% | nos | 18 | 2000 | 36000
27 | 4 Way DB | 4 Way DB | 4 Way DB | 100% | nos | 13 | 300 | 3900
28 | Timer And Connector | Timer And Connector | Timer And Connector | 100% | nos | 5 | 8000 | 40000
29 | 400 AMP Auto Changeover | 400 AMP Auto Chengower | 400 AMP Auto Chengower | 100% | nos | 1 | 61000 | 61000
30 | 1100 AMP Bus Bar | 1100 AMP Bus Bar | 1100 AMP Bus Bar | 100% | nos | 1 | 16000 | 16000 | 107037.8 | 11131931.2
31 | Lift Electric Work | Lift Electric Work | Lift Electric Work | 100% | nos | 10 | 17000 | 170000 | 110036.18 | 5721881.36
32 | Light Fixture Fitting | Light Fixture Fiting | Light Fixture Fiting | 100% | nos | 1535 | 50 | 76750
33 | Fan Fitting With Hook & Pipe | Fen Fiting With Hook & Pipe | Fen Fiting With Hook & Pipe | 100% | nos | 18 | 200 | 3600
34 | Neon And Profile Light Fitting | Neon And Profile Light Fiting | Neon And Profile Light Fiting | 100% | mtr | 253 | 80 | 20240
35 | 25sqmm Earthing Cable | 25sqmm Erathing Cable | 25sqmm Erathing Cable | 100% | mtr | 143 | 90 | 12870
36 | 25X3 GI Earthing Strip | 25X3 GI Erathing Strip | 25X3 GI Erathing Strip | 100% | mtr | 300 | 90 | 27000
37 | Lighting Arrester | Lightning Arrester | Lightning Arrester | 100% | nos | 5 | 1900 | 9500
38 | 380 X 280 X 130 JB | 380 X 280 X 130 JB | 380 X 280 X 130 JB | 100% | nos | 4 | 4200 | 16800
39 | 380 X 190 X 130 JB | 380 X 190 X 130 JB | 380 X 190 X 130 JB | 100% | nos | 7 | 2245 | 15715
40 | 180 X 180 X 100 JB | 180 X 180 X 100 JB | 180 X 180 X 100 JB | 100% | nos | 8 | 1200 | 9600
41 | 100 X 100 X 75 JB | 100 X 100 X 75 JB | 100 X 100 X 75 JB | 100% | nos | 60 | 550 | 33000
| Total Bill Amount | [6 empty] | 2843499
| CGST @ 9% | [6 empty] | 255914.91
| SGST @ 9% | [6 empty] | 255914.91
3355328.82
Thirty Three Lakh Fifty Five Thousand Three Hundred Twenty Nine Only
| Advance Payment | [6 empty] | 0
| Retention @ 5% to be deducted | [6 empty] | 0
| Balance Payment to be paid | [6 empty] | 3355328.82
TDS will be deducted as per applicable rules at your end
Approved By -