## Bill-1
Payment Certificate
Company Name |  | NIJANAND CONSTRUCTION |  |  | Invoice No.
Vendor Name |  | Manojbhai
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - |  | 2025-03-24
Type of Work - |  | Road Trimix Labour Work |  |  | Bill Date |  | 2025-03-06
Type of Contract - |  | Road Trimix Labour Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Nos. | Rate | Amount
1 | Basement-1 Trimix work with steel and Groove cutting |  | 100% | 31131 | Sq.ft. | 1 | 10 | 311310
2 | Basement-2 Trimix work with steel and Groove cutting |  | 100% | 35910 | Sq.ft. | 1 | 6.75 | 242392.5
| Total Bill Amount | [6 empty] | 553702.5
| Central GST 9% | [6 empty] | 49833.225
| State GST 9% | [6 empty] | 49833.225
Debit
653368.95
Six Lakh Fifty Three Thousand Three Hundred Sixty Nine Only
Advance Payment
Retention 5%
| Balance Payment to be paid | [6 empty] | 653368.95
Approved By -

## Bill-2
Payment Certificate
Company Name |  | NIJANAND CONSTRUCTION |  |  | Invoice No.
Vendor Name |  | Manojbhai
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - |  | 2025-07-01
Type of Work - |  | Road Trimix Labour Work |  |  | Bill Date |  | 2025-07-01
Type of Contract - |  | Road Trimix Labour Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Nos. | Rate | Amount
1 | Ground floor Area Road Trimix Work |  | 100% | 14103 | Sq.ft. | 1 | 18 | 253854
2 | Both Ramp, Multipurpose court, Children Play Area trimix work |  | 100% | 4730 | Sq.ft. | 1 | 10 | 47300
3 | Parking entry and Backside area PCC work (Leveling and GSB work with Slope) |  | 100% | 2234 | Sq.ft. | 1 | 12 | 26808
| Total Bill Amount | [6 empty] | 327962
| Central GST 9% | [6 empty] | 29516.58
| State GST 9% | [6 empty] | 29516.58
| Debit | [6 empty] | 61000 | 50000 | Delay
[8 empty] | 325995.16 | 11000 | Creck
Three Lakh Twenty Five Thousand Nine Hundred Ninty Five Only
Advance Payment
Retention 5%
| Balance Payment to be paid | [6 empty] | 325995.16
Approved By -

## Bill-3
Payment Certificate
Company Name |  | Mahesh M Savaliya |  |  | Invoice No.
Vendor Name |  | Manojbhai
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - |  | 2025-07-01
Type of Work - |  | Labour Supply Work |  |  | Bill Date |  | 2025-07-01
Type of Contract - |  | Labour Supply Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Nos. | Rate | Amount
1 | Depart Labour for Basement Cleaning and Road Cleaning work |  | 100% | 1 | Sq.ft. | 66 | 600 | 39600
| Total Bill Amount | [6 empty] | 39600
| Central GST 9% | [6 empty] | 0
| State GST 9% | [6 empty] | 0
Debit
39600
Thirty Nine Thousand Six Hundred Only
Advance Payment
Retention 5%
| Balance Payment to be paid | [6 empty] | 39600
Approved By -