## 1
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-1
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2022-10-05
Type of Work - |  | Retaining wall water proofing work |  |  | Bill Date | 2022-08-09
Type of Contract - |  | With material water proofing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | Crystaline Coating work |  | 100% | 3287.9 | Sq.ft. | 40 | 131516 | 953729.808
| Total Bill Amount | [5 empty] | 131516
| GST @ 18% | [5 empty] | 23672.88
155188.88
One lakh Fifty Five Thousand One Hundred Eighty Nine Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 7759.444
| Balance Payment to be paid | [5 empty] | 147429.436
TDS will be deducted as per applicable rules at your end
Approved By -

## 2
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-2
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2023-01-12
Type of Work - |  | Retaining wall water proofing work |  |  | Bill Date | 2023-01-01
Type of Contract - |  | With material water proofing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | Crystaline Coating work |  | 100% | 5199.02 | Sq.ft. | 40 | 207960.8
2 | Expantion Joint belt work |  | 100% | 14.1 | R.mt. | 2200 | 31020 | 18629.84
| Total Bill Amount | [5 empty] | 238980.8
| GST @ 18% | [5 empty] | 43016.544
281997.344
Two Lakh Eighty One Thousand Nine Hundred Ninty Seven Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 14099.8672
| Balance Payment to be paid | [5 empty] | 267897.4768
TDS will be deducted as per applicable rules at your end
Approved By -

## 3
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-3
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2023-06-22
Type of Work - |  | Retaining wall water proofing work |  |  | Bill Date | 2023-08-31
Type of Contract - |  | With material water proofing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | Crystaline Coating work |  | 100% | 10142.92 | Sq.ft. | 40 | 405716.8
2 | Expantion Joint belt work |  | 100% | 14.56 | R.mt. | 2200 | 32032 | 23573.74
| Total Bill Amount | [5 empty] | 437748.8
| GST @ 18% | [5 empty] | 78794.784
516543.584
Five Lakh Sixteen Thousand Five Hundred Forty Four Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 25827.1792
| Balance Payment to be paid | [5 empty] | 490716.4048
TDS will be deducted as per applicable rules at your end
Approved By -

## 4
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-4
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-01-20
Type of Work - |  | Retaining wall water proofing work |  |  | Bill Date | 2024-01-19
Type of Contract - |  | With material water proofing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | Terrace PU Coating work (D-Tower, Lift Top, Tank Top) |  | 100% | 3767.65 | Sq.ft. | 70 | 263735.5
2 | OHWT Vertical Wall Crystaline Coating work |  | 100% | 159.81 | Sq.ft. | 40 | 6392.4
3 | Staircase Coating work |  | 100% | 468 | R.MT. | 55 | 25740
| Total Bill Amount | [5 empty] | 295867.9
| GST @ 18% | [5 empty] | 53256.222
349124.122
Three Lakh Fourty Nine Thousand One Hundred Twenty Four Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 17456.2061
| Balance Payment to be paid | [5 empty] | 331667.9159
TDS will be deducted as per applicable rules at your end
Approved By -

## 6
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-6
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-03-08
Type of Work - |  | Terrace Water proofing work |  |  | Bill Date | 2024-03-06
Type of Contract - |  | Terrace Water proofing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | PU Coating work (D- Tower Water tank) |  | 100% | 3583.65 | Sq.ft. | 70 | 250855.5
2 | Crystaline Coating work (Tnak Wall) |  | 100% | 159.81 | Sq.ft. | 40 | 6392.4
| Total Bill Amount | [5 empty] | 257247.9
| GST @ 18% | [5 empty] | 46304.622
303552.522
Three Lakh Three Thousand Five Hundred Fifty Two Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -

## 7
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-7
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-03-08
Type of Work - |  | Flat coating work |  |  | Bill Date | 2024-03-05
Type of Contract - |  | Flat coating work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | Flat Internal Coating work (Flat No. 1212, 611, 811, 1112, 912, 812, 712, 612, 1012) |  | 100% | 12620 | Sq.ft. | 35 | 441700
| Total Bill Amount | [5 empty] | 441700
| GST @ 18% | [5 empty] | 79506
521206
Five Lakh Twenty One Thousand Two Hundred Six Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -

## 8
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-8
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-05-07
Type of Work - |  | BBC Work |  |  | Bill Date | 2024-04-29
Type of Contract - |  | BBC Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | D- Building BBC work (Terrace) |  | 100% | 7486.92 | Sq.ft. | 22 | 164712.24
| Total Bill Amount | [5 empty] | 164712.24
| GST @ 18% | [5 empty] | 29648.2032
194360.4432
One Lakh Ninty Four Thousand Three Hundred Sixty Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -

## 9
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-9
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-06-08
Type of Work - |  | BBC Work |  |  | Bill Date | 2024-06-05
Type of Contract - |  | BBC Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | C- Building BBC work (Terrace) |  | 100% | 6784.38 | Sq.ft. | 22 | 149256.36
2 | PU Coating Work |  | 100% | 6590.1 | Sq.ft. | 70 | 461307
3 | Crystaline Coating work |  | 100% | 194.28 | Sq.ft. | 40 | 7771.2
| Total Bill Amount | [5 empty] | 618334.56
| GST @ 18% | [5 empty] | 111300.2208
729634.7808
Seven Lakh Twenty Nine Thousand Six Hundred Thirty Five Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -

## 10
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-10
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-06-08
Type of Work - |  | BBC Work |  |  | Bill Date | 2024-06-05
Type of Contract - |  | BBC Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | Flat Internal Coating work (Flat No. 1306, 1106, 1006, 806, 807, 706, 405, 406, 305, 306 and 1206, 906, 808, 605, 606, 506 Part area) C-Building |  | 100% | 16891.23 | Sq.ft. | 35 | 591193.05
| Total Bill Amount | [5 empty] | 591193.05
| GST @ 18% | [5 empty] | 106414.749
697607.799
Six Lakh Ninty Seven Thousand Six Hundred Eight Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -
This is to be debited from Dhavalbhai Contractor

## 11
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-11
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-06-08
Type of Work - |  | BBC Work |  |  | Bill Date | 2024-06-05
Type of Contract - |  | BBC Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | China Mosaic work D-Building Terrace |  | 100% | 6922.77 | Sq.ft. | 20 | 138455.4
2 | Crystaline Coating for Lift Pit D & E Building |  | 100% | 705.36 | Sq.ft. | 40 | 28214.4
3 | BBC Work D & E Building Lift Pit |  | 100% | 705.36 | Sq.ft. | 22 | 15517.92
4 | Staircase coating Work E- Building |  | 100% | 468 | R.mt. | 55 | 25740
| Total Bill Amount | [5 empty] | 207927.72
| GST @ 18% | [5 empty] | 37426.9896
245354.7096
Two Lakh Fourty Five Thousand Three Hundred Fifty Five Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -

## 12
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-12
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-08-17
Type of Work - |  | BBC and China Mosaic Work |  |  | Bill Date | 2024-08-07
Type of Contract - |  | BBC and China Mosaic Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | China Mosaic work C- Building Terrace |  | 100% | 6431.93 | Sq.ft. | 20 | 128638.6
2 | Crystaline Coating Work |  | 100% | 371.14 | Sq.ft. | 40 | 14845.6
3 | BBC work |  | 100% | 371.14 | Sq.ft. | 22 | 8165.08
| Total Bill Amount | [5 empty] | 151649.28
| GST @ 18% | [5 empty] | 27296.8704
178946.1504
One Lakh Seventy Eight Thousand Nine Hundred Fourty Six Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -

## 13
Payment Certificate
Company Name |  | Ramesh M. Chotaliya |  |  | Invoice No. |  | 1
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-09-26
Type of Work - |  | Terrace Cleaning work |  |  | Bill Date | 2024-09-24
Type of Contract - |  | Terrace Cleaning work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | Cleaning and removing Debris, Loose Concrete, Make surface cleaning of Terrace A & B Building |  | 100% | 1 | Lumsum | 35000 | 35000
| Total Bill Amount | [5 empty] | 35000
| GST @ 18% | [5 empty] | 0
35000
Thirty Five Thousand Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -
Debit from Dhavalbhai

## 13-1
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-13
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-09-26
Type of Work - |  | PU Coating and Crystaline Coating work |  |  | Bill Date | 2024-09-24
Type of Contract - |  | PU Coating and Crystaline Coating work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | A- Building terrace, Water Tank, Duct top PU Coating work |  | 100% | 7250.86 | Sq.ft. | 70 | 507560.2
2 | Crystaline Coating Work Water Tank Pardi work |  | 100% | 502.5 | Sq.ft. | 40 | 20100
| Total Bill Amount | [5 empty] | 527660.2
| GST @ 18% | [5 empty] | 94978.836
622639.036
Six Lakh Twenty Two Thousand Six Hundred Thirty Nine Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -

## 14
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-14
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-09-26
Type of Work - |  | Coating for Flats |  |  | Bill Date | 2024-09-25
Type of Contract - |  | Coating for Flats
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | B- Building Flat Internal Coating work (Flat No. 1303, 1304, 1204, 1203, 1104, 1103, 1004, 1003, 904, 804, 803 (M1,CB,M2), 704, 703) |  | 100% | 13316 | Sq.ft. | 35 | 466060 | 1392941.9
| Total Bill Amount | [5 empty] | 466060
| GST @ 18% | [5 empty] | 83890.8
549950.8
Five Lakh Fourty Nine Thousand Nine Hundred Fifty One Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -
Debit from Dhavalbhai

## 15
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-15
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-12-13
Type of Work - |  | Coating for Flats |  |  | Bill Date | 2024-11-27
Type of Contract - |  | Coating for Flats
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | A & B- Building Flat Internal Coating work (Flat No. 603, 604, 303, 304, 1301, 1302, 1201, 1202, 1101, 1102, 701, 702, 501) |  | 100% | 13992 | Sq.ft. | 35 | 489720
2 | B 1303 Slab Crack Filling |  | 100% | 1 | Lumsum | 30000 | 30000
| Total Bill Amount | [5 empty] | 519720
| GST @ 18% | [5 empty] | 93549.6
613269.6
Six Lakh Thirteen Thousand Two Hundred Seventy only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -
Debit from Dhavalbhai

## 16
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-16
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2025-01-24
Type of Work - |  | Waterproofing, China mosaic, PU Coating work |  |  | Bill Date | 2025-01-10
Type of Contract - |  | Waterproofing, China mosaic, PU Coating work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | BBC Work |  | 100% | 10058.42 | Sq.ft. | 22 | 221285.24
2 | China Mosaic Work |  | 100% | 6923.13 | Sq.ft. | 20 | 138462.6
3 | Crystaline Coating work |  | 100% | 761.16 | Sq.ft. | 40 | 30446.4
4 | PU Coating work |  | 100% | 89.88 | Sq.ft. | 70 | 6291.6
5 | Staircase coating Work A & B- Building |  | 100% | 2940 | R.ft. | 55 | 161700
| Total Bill Amount | [5 empty] | 558185.84
| GST @ 18% | [5 empty] | 100473.4512
658659.2912
Six Lakh Fifty Eight Thousand Six Hundred Fifty Nine Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -
Debit from Dhavalbhai

## 17
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-17
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2025-01-24
Type of Work - |  | Flat Coating work |  |  | Bill Date | 2025-01-21
Type of Contract - |  | Flat Coating work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | A- Building Flat Internal Coating work (Flat No. 201, 202, 401, 402, 502 (L+K+S+C.Bed), 601, 602, 801, 802, 901, 902, 1001 (Bed 1 & 2), 1002 (Bed 1 & 2 + Kitchen) |  | 100% | 12490.34 | Sq.ft. | 35 | 437161.9
| Total Bill Amount | [5 empty] | 437161.9
| GST @ 18% | [5 empty] | 78689.142
515850.042
Five Lakh Fifteen Thousand Eight Hundred Fifty Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -
Debit from Dhavalbhai

## 18
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-18
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2025-02-20
Type of Work - |  | COP Area |  |  | Bill Date | 2025-02-12
Type of Contract - |  | COP Area
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | BBC Work |  | 100% | 7911.68 | Sq.ft. | 22 | 174056.96
2 | Core Cutting Gabda Filling work |  | 100% | 187 | Nos. | 600 | 112200
3 | Crystaline Coating Work Garden Flower bed |  | 100% | 1961.38 | Sq.ft. | 40 | 78455.2
4 | PU Coating work |  | 100% | 8661.23 | Sq.ft. | 70 | 606286.1
| Total Bill Amount | [5 empty] | 970998.26
| GST @ 18% | [5 empty] | 174779.6868
1145776.9468
Eleven Lakh Fourty Five Thousand Seven Hundred Seventy Seven Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -
Debit from Dhavalbhai

## 19
Payment Certificate
Company Name |  | Narayan Corporation |  |  | Invoice No. |  | RA Bill-19
Vendor Name |  | Girishbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2025-04-23
Type of Work - |  | COP Area |  |  | Bill Date | 2025-04-17
Type of Contract - |  | COP Area
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | BBC Work |  | 100% | 4585.21 | Sq.ft. | 22 | 100874.62
2 | Crystaline Coating Work Garden Flower bed |  | 100% | 3893.28 | Sq.ft. | 40 | 155731.2
3 | PU coating work |  | 100% | 4456.17 | Sq.ft. | 70 | 311931.9
4 | Expansion Joint work with belt |  | 100% | 54.88 | R.mt. | 2200 | 120736
5 | Geotextile Work |  | 100% | 7337.74 | Sq.ft. | 7 | 51364.18
6 | Drain Board Work |  | 100% | 7760.46 | Sq.ft. | 35 | 271616.1
| Total Bill Amount | [5 empty] | 1012254
| GST @ 18% | [5 empty] | 182205.72
1194458.72
Eleven Lakh Ninty Four Thousand Four Hundred Fifty Nine Only
| Advance Payment | [5 empty] | 0
Retention @ 5% to be deducted
Balance Payment to be paid
TDS will be deducted as per applicable rules at your end
Approved By -
Debit from Dhavalbhai