## 1
Payment Certificate
Company Name |  | Hina N. Shah |  |  | Invoice No. |  | 1
Vendor Name |  | Nisadhbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2023-10-24
Type of Work - |  | Plumbing Work C-Building |  |  | Bill Date | 2023-10-22
Type of Contract - |  | C- Building Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | Inlet fitting Work (1st, 2nd, 3rd Floor) |  | 100% | 12 | Nos. | 6800 | 81600
2 | Internal Drainage Work (1st, 2nd, 3rd Floor) |  | 100% | 12 | Nos. | 3400 | 40800
3 | Waterproofing work (1st, 2nd, 3rd Floor) |  | 100% | 12 | Nos. | 8500 | 102000
| Total Bill Amount | [5 empty] | 224400
| GST @ 18% | [5 empty] | 0
224400
Two Lakh Twenty Four Thousand Four Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 224400
TDS will be deducted as per applicable rules at your end
Approved By -

## 2
Payment Certificate
Company Name |  | Hina N. Shah |  |  | Invoice No. |  | 2
Vendor Name |  | Nisadhbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2023-01-03
Type of Work - |  | Plumbing Work C-Building |  |  | Bill Date | 2023-01-03
Type of Contract - |  | C- Building Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | Inlet fitting Work (4th (2 Flats), 5th, 6th (3 Flats), 7th (3 Flats) Floor) |  | 100% | 13 | Nos. | 6800 | 88400
2 | Internal Drainage Work (4th (2 Flats), 5th, 6th (3 Flats), 7th (3 Flats) Floor) |  | 100% | 13 | Nos. | 3400 | 44200
3 | Waterproofing work (4th (2 Flats), 5th, 6th (3 Flats), 7th (3 Flats) Floor) |  | 100% | 13 | Nos. | 8500 | 110500
| Total Bill Amount | [5 empty] | 243100
| GST @ 18% | [5 empty] | 0
243100
Two Lakh Fourty Thousand One Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 243100
TDS will be deducted as per applicable rules at your end
Approved By -

## 3
Payment Certificate
Company Name |  | Hina N. Shah |  |  | Invoice No. |  | 3
Vendor Name |  | Nisadhbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-01-27
Type of Work - |  | Plumbing Work C-Building |  |  | Bill Date | 2024-01-25
Type of Contract - |  | C- Building Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | Inlet fitting Work 8th floor (4 Flats) |  | 100% | 4 | Nos. | 6800 | 27200
| Total Bill Amount | [5 empty] | 27200
| GST @ 18% | [5 empty] | 0
27200
Twenty Seven Thousand Two Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 27200
TDS will be deducted as per applicable rules at your end
Approved By -

## 4
Payment Certificate
Company Name |  | Hina N. Shah |  |  | Invoice No. |  | 4
Vendor Name |  | Nisadhbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-01-27
Type of Work - |  | Plumbing Work C-Building |  |  | Bill Date | 2024-03-01
Type of Contract - |  | C- Building Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
C- Tower Flat No. 905, 906, 907, 908, 1008, 1007, 1108, 1107, 1208, 1207 (10 Flats)
1 | Inlet fitting Work (9th, 10th, 11th, 12th (10 Flats) |  | 100% | 10 | Nos. | 6800 | 68000
A- Tower Flat No. 201, 202, 301, 302, 401, 402 (6 Flats)
1 | Inlet fitting Work (2nd, 3rd, 4th) (4 Flats) |  | 100% | 4 | Nos. | 6800 | 27200
| Total Bill Amount | [5 empty] | 95200
| GST @ 18% | [5 empty] | 0
95200
Ninty Five Thousand Two Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 95200
TDS will be deducted as per applicable rules at your end
Approved By -

## 5
Payment Certificate
Company Name |  | Hina N. Shah |  |  | Invoice No. |  | 5
Vendor Name |  | Nisadhbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-06-08
Type of Work - |  | Plumbing Work C-Building |  |  | Bill Date | 2024-06-01
Type of Contract - |  | C- Building Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
C-Tower
1 | 107 and 108 Side OTS work |  | 100% | 13 | Nos. | 6800 | 88400
2 | Inlet fitting Work (1307 & 1308) (2 Flats) |  | 100% | 2 | Nos. | 6800 | 13600
3 | Internal Drainage Work (807, 808, 907, 908, 1007, 1008, 1207, 1208, 1307, 1308, 1107, 1108- 12 Flats) |  | 100% | 12 | Nos. | 3400 | 40800
4 | Waterproofing work (807, 808, 907, 908, 1007, 1008, 1207, 1208, 1307, 1308, 1107, 1108- 12 Flats) |  | 100% | 12 | Nos. | 8500 | 102000
| Total Bill Amount | [5 empty] | 244800
| GST @ 18% | [5 empty] | 0
244800
Two Lakh Fourty Four Thousand Eight Hundred only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 244800
TDS will be deducted as per applicable rules at your end
Approved By -

## 6
Payment Certificate
Company Name |  | Hina N. Shah |  |  | Invoice No. |  | 2
Vendor Name |  | Nisadhbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-07-13
Type of Work - |  | Plumbing Work C-Building |  |  | Bill Date | 2024-07-05
Type of Contract - |  | C- Building Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
C-Tower
1 | Inlet fitting Work (1005, 1006, 1105, 1106, 1205, 1206, 1305, 1306) (8 Flats) |  | 100% | 8 | Nos. | 6800 | 54400
2 | Internal Drainage Work (805, 806, 905, 906, 1005, 1006, 1105, 1106, 1205, 1206, 1305, 1306) (12 Flats) |  | 100% | 12 | Nos. | 3400 | 40800
3 | Waterproofing work (805, 806, 905, 906, 1005, 1006, 1105, 1106, 1205, 1206,1305, 1306) (12 Flats) |  | 100% | 12 | Nos. | 8500 | 102000
4 | 105 and 108 Side OTS work |  | 100% | 3 | OTS | 29471 | 88413
| Total Bill Amount | [5 empty] | 285613
| GST @ 18% | [5 empty] | 0
285613
Two Lakh Eighty Five Thousand Six Hundred Thirteen Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 285613
TDS will be deducted as per applicable rules at your end
Approved By -

## 7
Payment Certificate
Company Name |  | Hina N. Shah |  |  | Invoice No. |  | 4
Vendor Name |  | Nisadhbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-09-07
Type of Work - |  | Plumbing Work C-Building |  |  | Bill Date | 2024-09-01
Type of Contract - |  | C- Building Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
C-Tower
1 | External Vertical Line Work OTS 105 Nos. Side (1 OTS) |  | 100% | 1 | Nos. | 29471 | 29471
2 | External Vertical Line Work OTS 106 Nos. Side (3 OTS) |  | 100% | 3 | Nos. | 29471 | 88413
3 | External Vertical Line Work OTS 107 Nos. Side (1 OTS) |  | 100% | 1 | Nos. | 29471 | 29471
4 | External Vertical Line Work OTS 108 Nos. Side (1 OTS) |  | 100% | 1 | OTS | 29471 | 29471
| Total Bill Amount | [5 empty] | 176826
| GST @ 18% | [5 empty] | 0
176826
One Lakh Seventy Six Thousand Eight Hundred Twenty Six Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 176826
TDS will be deducted as per applicable rules at your end
Approved By -

## 8
Payment Certificate
Company Name |  | Hina N. Shah |  |  | Invoice No. |  | 5
Vendor Name |  | Nisadhbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-09-07
Type of Work - |  | Plumbing Work A-Building |  |  | Bill Date | 2024-09-01
Type of Contract - |  | A- Building Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
A-Tower
1 | Inlet Fitting Works 101, 102, 502, 601, 602, 702, 801, 802, 901, 902, 1001, 1002, 1101, 1102, 1201, 1202, 1301, 1302 |  | 100% | 18 | Nos. | 6800 | 122400
2 | Previous Bill Pending Flat 201, 301 Inlet Fitting work |  | 100% | 2 | Nos. | 6800 | 13600
| Total Bill Amount | [5 empty] | 136000
| GST @ 18% | [5 empty] | 0
136000
One Lakh Thirty Six Thousand Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 136000
TDS will be deducted as per applicable rules at your end
Approved By -

## 9
Payment Certificate
Company Name |  | Hina N. Shah |  |  | Invoice No. |  | 8
Vendor Name |  | Nisadhbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-09-25
Type of Work - |  | Plumbing Work A-Building |  |  | Bill Date | 2024-09-23
Type of Contract - |  | A- Building Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
A-Tower
1 | External Plumbing work (20%) (26- Flats) |  | 100% | 26 | Nos. | 6800 | 176800
| Total Bill Amount | [5 empty] | 176800
| GST @ 18% | [5 empty] | 0
176800
One Lakh Seventy Six Thousand Eight Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 176800
TDS will be deducted as per applicable rules at your end
Approved By -

## 10
Payment Certificate
Company Name |  | Hina N. Shah |  |  | Invoice No. |  | 10
Vendor Name |  | Nisadhbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-09-25
Type of Work - |  | Plumbing Work A-Building |  |  | Bill Date | 2024-09-25
Type of Contract - |  | A- Building Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
A-Tower
1 | Internal Drainage work (10%) (23- Flats) |  | 100% | 23 | Nos. | 3400 | 78200
| Total Bill Amount | [5 empty] | 78200
| GST @ 18% | [5 empty] | 0
78200
Seventy Eight Thousand Two Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 78200
TDS will be deducted as per applicable rules at your end
Approved By -

## 11
Payment Certificate
Company Name |  | Hina N. Shah |  |  | Invoice No. |  | 11
Vendor Name |  | Nisadhbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-09-25
Type of Work - |  | Plumbing Work A-Building |  |  | Bill Date | 2024-09-25
Type of Contract - |  | A- Building Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
A-Tower
1 | Waterproofing work (25%) (23- Flats) |  | 100% | 23 | Nos. | 8500 | 195500
| Total Bill Amount | [5 empty] | 195500
| GST @ 18% | [5 empty] | 0
195500
One Lakh Ninty Five Thousand Five hundred only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 195500
TDS will be deducted as per applicable rules at your end
Approved By -

## 12
Payment Certificate
Company Name |  | Hina N. Shah |  |  | Invoice No. |  | 12
Vendor Name |  | Nisadhbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2024-12-05
Type of Work - |  | Plumbing Work A-Building |  |  | Bill Date | 2024-12-04
Type of Contract - |  | A- Building Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
A-Tower
1 | Terrace Looping work (10% of Total Cost) |  | 100% | 26 | Nos. | 3400 | 88400
| Total Bill Amount | [5 empty] | 88400
| GST @ 18% | [5 empty] | 0
88400
Eighty Eight Thousand Four Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 88400
TDS will be deducted as per applicable rules at your end
Approved By -

## 13
Payment Certificate
Company Name |  | Hina N. Shah |  |  | Invoice No. |  | 13
Vendor Name |  | Nisadhbhai
To, Tanvi Infracon - Pramukh Revanta Project |  |  |  |  | Date - | 2025-03-01
Type of Work - |  | Plumbing Work C-Building |  |  | Bill Date | 2025-01-27
Type of Contract - |  | C- Building Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
C-Tower
1 | C.P. Fitting 7.5% (45 Nos.) |  | 100% | 45 | Nos. | 2550 | 114750
2 | Sanitary Fitting 7.5% (45 Nos.) |  | 100% | 45 | Nos. | 2550 | 114750
3 | Waterproofing and Coating in Naked flat (15%)(3 Flats) |  | 100% | 3 | Nos. | 5100 | 15300
| Total Bill Amount | [5 empty] | 244800
| GST @ 18% | [5 empty] | 0
244800
Two Lakh Fourty Four Thousand Eight Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 244800
TDS will be deducted as per applicable rules at your end
Approved By -