## Bill-1
Payment Certificate
Company Name |  | Abdullah Ibarahim |  |  | Invoice No. |  | 5
Vendor Name |  | Rahemanbhai
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2024-08-17
Type of Work - |  | Colour, Internal putty and Primer work |  |  | Bill Date | 2024-08-10
Type of Contract - |  | Colour work in labour
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate | Amount
1 | D & E- Building Outer Colour Work |  | 100% | 87640 | Sq.ft. | 4.5 | 394380
2 | D & E- Building Duct wall and Pipe One coat primer and Two coat Colour work |  | 100% | 27739 | Sq.ft. | 3.5 | 97086.5
3 | C- Building Outer Primer Work (Two Coat) |  | 100% | 85484 | Sq.ft. | 2 | 170968
4 | C- Building Duct wall and Pipe One coat primer |  | 100% | 20298 | Sq.ft. | 1.5 | 30447
5 | D & E- Building Lift and Passage Ceiling One coat Colour work |  | 100% | 5921 | Sq.ft. | 16 | 94736
6 | D & E- Building Staircase and Balcony Putty and One Coat Primer work |  | 100% | 9405 | Sq.ft. | 5 | 47025
7 | D & E- Building Texture One coat Primer work |  | 100% | 9405 | Sq.ft. | 1.25 | 11756.25
8 | D- Building One Coat Internal Primer work in Flat |  | 100% | 59779.75 | Sq.ft. | 2 | 119559.5
9 | E- Building One Coat Internal Primer work in Flat |  | 100% | 38259.04 | Sq.ft. | 2 | 76518.08
10 | C, D and E Internal Primer Lift Duct One coat Primer work |  | 100% | 23052 | Sq.ft. | 1.25 | 28815
| Total Bill Amount | [5 empty] | 1071291.33
| Central GST 9% | [5 empty] | 96416.2197 | 5250442.1078
| State GST 9% | [5 empty] | 96416.2197 | 1264124
| Debit | [6 empty] | 605655
[7 empty] | 1264123.7694 | 598184
| Twelve Lakh Sixty Four Thousand One Hundred Twenty Four Only | [6 empty] | 943508
| Advance Payment | [6 empty] | 553063
| Retention 5% | [5 empty] | 63206.1885 | 550034
| Balance Payment to be paid | [5 empty] | 1200917.5809 | 521031
74286
478666
678168
641038
Approved By - | [7 empty] | 12158199.1078
0

## Bill-2
Payment Certificate
Company Name |  | Abdullah Ibarahim |  |  | Invoice No. |  | 9
Vendor Name |  | Rahemanbhai
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2024-09-27
Type of Work - |  | Colour, Internal putty and Primer work |  |  | Bill Date | 2024-09-25
Type of Contract - |  | Colour work in labour
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate | Amount
1 | C- Building Internal Single coat primer (44 Flats) |  | 100% | 118465.16 | Sq.ft. | 2 | 236930.32
2 | C- Building Staircase Ceiling Birla Putty Two Coat |  | 100% | 2574 | Sq.ft. | 3 | 7722
3 | C- Building Staircase Duct Final Colour Work |  | 100% | 3682 | Sq.ft. | 3.5 | 12887
4 | C- Building Duct wall and Pipe One coat primer |  | 100% | 20298 | Sq.ft. | 2 | 40596
5 | C- Building One Coat Colour Work |  | 100% | 85484 | Sq.ft. | 1.5 | 128226
6 | D & E Building Duct Grill Final Colour Work |  | 100% | 2340 | Sq.ft. | 4 | 9360
7 | D & E- Building Lift Passage Putty and One Coat Colour work |  | 100% | 8168.46 | Sq.ft. | 10 | 81684.6
8 | D & E- Building Staircase ceiling one coat colour work |  | 100% | 9404 | Sq.ft. | 1 | 9404
9 | D & E Staircaase Texture One Coat Colour Work |  | 100% | 9405 | Sq.ft. | 1.25 | 11756.25
10 | D & E Building Terrace Staircase One coat Primer and Colour Work |  | 100% | 686 | Sq.ft. | 2.5 | 1715
| Total Bill Amount | [5 empty] | 540281.17
| Central GST 9% | [5 empty] | 48625.3053
| State GST 9% | [5 empty] | 48625.3053
Debit
637531.7806
Six Lakh Thirty Seven Thousand Five Hundred Thirty Two Only
Advance Payment
| Retention 5% | [5 empty] | 31876.589
| Balance Payment to be paid | [5 empty] | 605655.1916
Approved By -

## Bill-3
Payment Certificate
Company Name |  | Abdullah Ibarahim |  |  | Invoice No. |  | 10
Vendor Name |  | Rahemanbhai
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2024-12-04
Type of Work - |  | Colour, Internal putty and Primer work |  |  | Bill Date | 2024-12-02
Type of Contract - |  | Colour work in labour
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate | Amount
1 | A & B Building Two Coat Primer One Coat Colour |  | 100% | 87640 | Sq.ft. | 3 | 262920
2 | A & B Building Duct Colour and Pipe Colour Two Coat Primer One coat Colour |  | 100% | 27739 | Sq.ft. | 2.5 | 69347.5
3 | A, B, C Building duct platform oil paint work |  | 100% | 6916 | Sq.ft. | 4 | 27664
4 | C- Building Staircase and balcony Two coat ceiling putty work and one coat colour |  | 100% | 6514.85 | Sq.ft. | 5 | 32574.25
5 | C- Building Staircase ceiling Two coat Putty and one coat colour work |  | 100% | 2574 | Sq.ft. | 3 | 7722
6 | C- Building Staircase Ceiling One coat colour |  | 100% | 3290 | Sq.ft. | 16 | 52640
7 | C- Building Lift Passage Putty work |  | 100% | 5380.99 | Sq.ft. | 8 | 43047.92
8 | C- Building Texture wall One coat colour |  | 100% | 4409 | Sq.ft. | 2.5 | 11022.5
| Total Bill Amount | [5 empty] | 506938.17
| Central GST 9% | [5 empty] | 45624.4353
| State GST 9% | [5 empty] | 45624.4353
Debit
598187.0406
Five Lakh Ninty Eight Thousand One Hundred Eighty Seven Only
Advance Payment
| Retention 5% | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 598187.0406
Approved By -

## Bill-4
Payment Certificate
Company Name |  | Abdullah Ibarahim |  |  | Invoice No. |  | 12
Vendor Name |  | Rahemanbhai
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2025-03-01
Type of Work - |  | Colour, Internal putty and Primer work |  |  | Bill Date | 2025-03-01
Type of Contract - |  | Colour work in labour
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate | Amount
1 | Basement-1 Birla Putty work |  | 100% | 50746 | Sq.ft. | 4 | 202984
2 | Basement-2 Birla Putty work |  | 100% | 50746 | Sq.ft. | 4 | 202984
3 | Basement 1 & 2 Ceiling white colour one coat work |  | 100% | 72030 | Sq.ft. | 2 | 144060
4 | D- Building Internal Primer Final coat work |  | 100% | 59779 | Sq.ft. | 1.5 | 89668.5
5 | E- Building Internal Primer Final coat work |  | 100% | 38259 | Sq.ft. | 1.5 | 57388.5
6 | D- Building Creak filling work |  | 100% | 25 | Nos. | 2500 | 62500
7 | E- Building Creak filling work |  | 100% | 16 | Nos. | 2500 | 40000
2 | Basement-2 Birla Putty work |  | 100% | 50746 | Sq.ft. | 4 | 202984
3 | Basement 1 & 2 Ceiling white colour one coat work |  | 100% | 72030 | Sq.ft. | 2 | 144060
4 | D- Building Internal Primer Final coat work |  | 100% | 59779 | Sq.ft. | 1.5 | 89668.5
5 | E- Building Internal Primer Final coat work |  | 100% | 38259 | Sq.ft. | 1.5 | 57388.5
6 | D- Building Creak filling work |  | 100% | 25 | Nos. | 2500 | 62500
7 | E- Building Creak filling work |  | 100% | 16 | Nos. | 2500 | 40000
| Total Bill Amount | [5 empty] | 1396186
| Central GST 9% | [5 empty] | 125656.74
| State GST 9% | [5 empty] | 125656.74
Debit
1647499.48
Nine Lakh Fourty Three Thousand Five Hundred Ten Only
Advance Payment
| Retention 5% | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 1647499.48
Approved By -

## Bill-5
Payment Certificate
Company Name |  | Abdullah Ibarahim |  |  | Invoice No. |  | 12
Vendor Name |  | Rahemanbhai
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2025-03-01
Type of Work - |  | Colour, Internal putty and Primer work |  |  | Bill Date | 2025-03-01
Type of Contract - |  | Colour work in labour
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate | Amount
1 | D & E Building Staircase Birla putty Colour work |  | 100% | 9405 | Sq.ft. | 1.7 | 15988.5
2 | D & E Building Lift Passage Ceiling final colour work |  | 100% | 5921 | Sq.ft. | 8 | 47368
3 | D & E Building staircase texture final colour work |  | 100% | 9954 | Sq.ft. | 1.5 | 14931
4 | B- Building Internal Primer one coat (24 Flats) |  | 100% | 57384 | Sq.ft. | 2 | 114768
5 | A & B Building Staircase and Balcony Birla putty work |  | 100% | 9405 | Sq.ft. | 3 | 28215
6 | A & B Building Lift primer One coat |  | 100% | 23052 | Sq.ft. | 1.25 | 28815
7 | D & E Building Lift passage wall colour work |  | 100% | 8168.46 | Sq.ft. | 5 | 40842.3
8 | D & E Building Terrace Staircase wall colour work |  | 100% | 686 | Sq.ft. | 1.5 | 1029
9 | A, B, D, E Staircase base grill colour |  | 100% | 21247 | Sq.ft. | 3 | 63741
10 | A, B, C, D & E - Building Entry ceiling birla putty work (26 + 52 Flats) |  | 100% | 1000 | Sq.ft. | 3 | 3000
11 | C- Building Internal Creak filling work |  | 100% | 44 | Flats | 2500 | 110000
| Total Bill Amount | [5 empty] | 468697.8
| Central GST 9% | [5 empty] | 42182.802
| State GST 9% | [5 empty] | 42182.802
Debit
553063.404
Five Lakh Fifty Three Thousand Sixty Three Only
Advance Payment
| Retention 5% | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 553063.404
Approved By -

## Bill-6
Payment Certificate
Company Name |  | Abdullah Ibarahim |  |  | Invoice No. |  | 2
Vendor Name |  | Rahemanbhai
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2025-06-01
Type of Work - |  | Colour, Internal putty and Primer work |  |  | Bill Date | 2025-06-01
Type of Contract - |  | Colour work in labour
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate | Amount
1 | D & E- Building Final Outer Colour Work |  | 100% | 87640 | Sq.ft. | 1.25 | 109550
2 | Basement Ceiling Final Colour work |  | 100% | 72030 | Sq.ft. | 1 | 72030
3 | C- Building Outer Colour Work |  | 100% | 85484 | Sq.ft. | 1.25 | 106855
4 | C- Building Internal Primer Final |  | 100% | 118465.16 | Sq.ft. | 1.5 | 177697.74
| Total Bill Amount | [5 empty] | 466132.74
| Central GST 9% | [5 empty] | 41951.9466
| State GST 9% | [5 empty] | 41951.9466
Debit
550036.6332
Five Lakh Fifty Thousand Thirty Seven Only
Advance Payment
| Retention 5% | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 550036.6332
Approved By -