## 1
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 204
Vendor Name |  | Jaber
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2023-05-09
Type of Work - |  | Plumbing Work |  |  | Bill Date | 2023-05-05
Type of Contract - |  | Inlet Plumbing work, Waterproofing Work & Drainage work (E- Building)
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | Toilet, Kitchen, Wash area Inlet Fitting (20%) (1st Floor) |  | 100% | 2 | Flat | 6380 | 12760
2 | Toilet, Kitchen, Wash area Internal Drainage Work (10%) (1st Floor) |  | 100% | 2 | Flat | 3190 | 6380
3 | Toilet, wash area Waterproofing and PCC work (25%) (1st Floor) |  | 100% | 2 | Flat | 7975 | 15950
| Total Bill Amount | [5 empty] | 35090
| GST @ 18% | [5 empty] | 0
35090
Thirty Five Thousand Ninty Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 35090
TDS will be deducted as per applicable rules at your end
Approved By -

## 2
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 185
Vendor Name |  | Jaber
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2024-03-11
Type of Work - |  | Plumbing Work |  |  | Bill Date | 2024-03-10
Type of Contract - |  | Plant water supply line work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | 1" UPVC Line fitting work (For D- Building) |  | 100% | 380 | R.ft. | 30 | 11400
2 | 1" UPVC Line fitting work (For Plant) |  | 100% | 700 | R.ft. | 30 | 21000
3 | Water tank fitting work |  | 100% | 3 | Nos. | 3500 | 10500
| Total Bill Amount | [5 empty] | 42900
| GST @ 18% | [5 empty] | 0
42900
Fourty Two Thousand Nine Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 42900
TDS will be deducted as per applicable rules at your end
Approved By -

## 3
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 208
Vendor Name |  | Jaber
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2024-06-08
Type of Work - |  | Plumbing Work |  |  | Bill Date | 2024-06-07
Type of Contract - |  | Inlet Plumbing work, Waterproofing Work & Drainage work (D & E- Building)
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | D and E Building Terrace looping work |  | 100% | 52 | Flat | 3200 | 166400
| Total Bill Amount | [5 empty] | 166400
| GST @ 18% | [5 empty] | 0
166400
One Lakh Sixty Six Thousand Four Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 166400
TDS will be deducted as per applicable rules at your end
Approved By -

## 4
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 214
Vendor Name |  | Jaber
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2024-08-16
Type of Work - |  | Plumbing Work |  |  | Bill Date | 2024-08-10
Type of Contract - |  | Inlet Plumbing work, Waterproofing Work & Drainage work (D & E- Building)
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
1 | D- Building ARV and PRV Fitting work (84 Valve) |  | 100% | 1 | Lumsum | 12000 | 12000
2 | 2nd Basement Storm water Line repairing work |  | 100% | 1 | Lumsum | 20000 | 20000
| Total Bill Amount | [5 empty] | 32000
| GST @ 18% | [5 empty] | 0
32000
Thirty Two Thousand Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 32000
TDS will be deducted as per applicable rules at your end
Approved By -

## 5
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 223
Vendor Name |  | Jaber
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2024-09-12
Type of Work - |  | Plumbing Work |  |  | Bill Date | 2024-09-10
Type of Contract - |  | Basement Drainage and Water supply line work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
Basement
1 | 6" Strom Water Line (Grey PVC - A, C, D, E Building Only) |  | 100% | 1013 | R.ft. | 90 | 91170
2 | 4" UPVC Water Supply Main Line Fitting |  | 100% | 1186 | R.ft. | 80 | 94880
3 | 3" UPVC Water Supply Building Ring Line Fitting |  | 100% | 1989 | R.ft. | 70 | 139230
| Total Bill Amount | [5 empty] | 325280
| GST @ 18% | [5 empty] | 0
325280
Three Lakh Twenty Five Thousand Two Hundred Eighty Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 325280
TDS will be deducted as per applicable rules at your end
Approved By -

## 6
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 224
Vendor Name |  | Jaber
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2024-09-25
Type of Work - |  | B- Building Plumbing Work |  |  | Bill Date | 2024-09-23
Type of Contract - |  | B- Building Plumbing Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
B-Building
1 | Outer Line Fitting work (20%) (26- Flats) |  | 100% | 26 | Flat | 6800 | 176800
2 | Inlet Fitting work (20%) (20 -Flats) |  | 100% | 20 | Flat | 6800 | 136000
3 | Waterproofing work (25%) (13 - Flats) |  | 100% | 13 | Flat | 8500 | 110500
4 | Internal Drainage work (10%) (13- Flats) |  | 100% | 13 | Flat | 3400 | 44200
| Total Bill Amount | [5 empty] | 467500
| GST @ 18% | [5 empty] | 0
467500
Four Lakh Sixty Seven Thousand Five Hundred only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 467500
TDS will be deducted as per applicable rules at your end
Approved By -

## 7
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 242
Vendor Name |  | Salauddin
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2024-11-20
Type of Work - |  | B- Building Plumbing Work |  |  | Bill Date | 2024-11-19
Type of Contract - |  | B- Building Plumbing Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
B-Building
1 | Inlet Fitting work (20%) (4 -Flats) |  | 100% | 4 | Flat | 6800 | 27200
2 | Waterproofing work (25%) (11 - Flats) |  | 100% | 11 | Flat | 8500 | 93500
3 | Internal Drainage work (10%) (11- Flats) |  | 100% | 11 | Flat | 3400 | 37400
4 | Terrace Looping Line Work (10%) (26- Flats) |  | 100% | 26 | Flat | 3400 | 88400
| Total Bill Amount | [5 empty] | 246500
| GST @ 18% | [5 empty] | 0
246500
Two lakh Fourty Six Thousand Five Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 246500
TDS will be deducted as per applicable rules at your end
Approved By -

## 8
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 250
Vendor Name |  | Salauddin
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2024-12-13
Type of Work - |  | B- Building Plumbing Work |  |  | Bill Date | 2024-12-10
Type of Contract - |  | B- Building Plumbing Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
B-Building
1 | Inlet Fitting work (20%) (1 -Flats) (203) |  | 100% | 1 | Flat | 6800 | 6800
2 | Waterproofing work (25%) (1 - Flats) (203) |  | 100% | 1 | Flat | 8500 | 8500
3 | Internal Drainage work (10%) (1- Flats) (203) |  | 100% | 1 | Flat | 3400 | 3400
| Total Bill Amount | [5 empty] | 18700
| GST @ 18% | [5 empty] | 0
18700
Eighteen Thousand Seven Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 18700
TDS will be deducted as per applicable rules at your end
Approved By -

## 9
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 254
Vendor Name |  | Salauddin
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2025-01-02
Type of Work - |  | Ground Floor Drainage work |  |  | Bill Date | 2024-12-29
Type of Contract - |  | Ground Floor Drainage work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
Ground Floor Drainage system
1 | 300 mm Dia. Pipe fitting work and P.C.C. |  | 100% | 500 | R.ft. | 150 | 75000
2 | 200 mm Dia. Pipe fitting work and P.C.C. |  | 100% | 480 | R.ft. | 110 | 52800
3 | 160 mm Dia. Pipe fitting work and P.C.C. |  | 100% | 60 | R.ft. | 90 | 5400
4 | 600 X 600 X 900 Chamber |  | 100% | 28 | Nos. | 3000 | 84000
5 | 300 X 300 X 900 Chamber |  | 100% | 13 | Nos. | 1800 | 23400
6 | 300 X 300 X 1200 Chamber |  | 100% | 6 | Nos. | 2200 | 13200
7 | 600 X 600 X 1200 Chamber |  | 100% | 14 | Nos. | 4000 | 56000
8 | Recharge Pit Chamber |  | 100% | 2 | Nos. | 15000 | 30000
| Total Bill Amount | [5 empty] | 339800
| GST @ 18% | [5 empty] | 0
339800
Three Lakah Thirty Nine Thousand Eight Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 339800
TDS will be deducted as per applicable rules at your end
Approved By -

## 10
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 256
Vendor Name |  | Salauddin
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2025-01-02
Type of Work - |  | D- Building Plumbing Work |  |  | Bill Date | 2024-12-29
Type of Contract - |  | D- Building Plumbing Work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate/ Flat | Amount
C.P. Fitting work
1 | C.P. fitting 7.5% |  | 100% | 21 | Flat | 2550 | 53550
2 | Sanitary fitting 7.5% |  | 100% | 21 | Flat | 2550 | 53550
| Total Bill Amount | [5 empty] | 107100
| GST @ 18% | [5 empty] | 0
107100
One Lakh Seven Thousand One Hundred Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 107100
TDS will be deducted as per applicable rules at your end
Approved By -

## 11
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 266
Vendor Name |  | Salauddin
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2025-02-25
Type of Work - |  | Basement and COP area line fitting C, D, E fitting |  |  | Bill Date | 2025-02-24
Type of Contract - |  | Basement and COP area line fitting C, D, E fitting
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate | Amount
Basement and COP area Line
1 | 110 mm Pipe fitting work |  | 100% | 858 | R.ft. | 80 | 68640
2 | 160 mm Pipe fitting work |  | 100% | 774 | R.ft. | 90 | 69660
3 | 50 mm Pipe fitting work |  | 100% | 475 | R.ft. | 50 | 23750
4 | 1 1/2" Pipe fitting work |  | 100% | 1556 | R.ft. | 30 | 46680
5 | 160 mm X 110 mm Connection fitting work |  | 100% | 40 | Nos. | 350 | 14000
6 | 1 1/4" X 1 1/2" Line connection work |  | 100% | 120 | Nos. | 150 | 18000
7 | 1 1/2" Ball Valve fitting work |  | 100% | 120 | Nos. | 150 | 18000
| Total Bill Amount | [5 empty] | 258730
| GST @ 18% | [5 empty] | 0
258730
Two Lakh Fifty Eight Thousand Seven Hundred Thirty Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 258730
TDS will be deducted as per applicable rules at your end
258730
Approved By -

## 12
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 288
Vendor Name |  | Salauddin
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2025-02-25
Type of Work - |  | Ground Floor |  |  | Bill Date | 2025-04-18
Type of Contract - |  | Ground Floor
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate | Amount
1 | Ground Floor Strom Water Line 12" |  | 100% | 397 | R.ft. | 150 | 59550
2 | Ground Floor Drainage Line Fitting 8" |  | 100% | 328 | R.ft. | 110 | 36080
3 | Ground Floor 600 X 600 Chamber |  | 100% | 10 | Nos. | 3000 | 30000
4 | Ground Floor 450 X 900 Chamber |  | 100% | 13 | Nos. | 3500 | 45500 |  | 66
5 | Ground Floor 300 X 300 Chamber |  | 100% | 12 | Nos. | 1800 | 21600
6 | Ground Floor Transformer to basement 6" Line fitting |  | 100% | 240 | R.ft. | 90 | 21600
7 | Boring to UGWT 2" Line fitting work |  | 100% | 265 | R.ft. | 50 | 13250
8 | ABC Building Basement
| 6" Pipe fitting |  | 100% | 99 | R.ft. | 90 | 8910
| 1 1/4" Pipe fitting |  | 100% | 1579 | R.ft. | 30 | 47370
| 4" Pipe fitting |  | 100% | 259 | R.ft. | 80 | 20720
| 2" Pipe fitting |  | 100% | 18 | R.ft. | 50 | 900
| 3" Pipe fitting |  | 100% | 8 | R.ft. | 70 | 560
| 1 1/2" Pipe fitting |  | 100% | 90 | R.ft. | 35 | 3150
| 80 mm Ring line fitting |  | 100% | 399.14 | R.ft. | 70 | 27939.8
| 1 1/2" Ball Valva fitting work |  | 100% | 100 | Nos. | 150 | 15000
9 | Ground floor Chamber cover fitting work (600 x 600 and 450 x 900) |  | 100% | 33 | Nos. | 300 | 9900
10 | Ground floor chamber cover fitting work (300 X 300) |  | 100% | 11 | Nos. | 200 | 2200
11 | Basement 600 X 600 Chamber cover fitting work |  | 100% | 18 | Nos. | 300 | 5400
| Total Bill Amount | [5 empty] | 369629.8 | 1293439.8
| GST @ 18% | [5 empty] | 0
369629.8
Three Lakh Sixty Nine Thousand Six Hundred Thirty Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 369629.8
TDS will be deducted as per applicable rules at your end
Approved By -

## 13
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 290
Vendor Name |  | Salauddin
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2025-02-25
Type of Work - |  | Flat Plumbing work |  |  | Bill Date | 2025-04-18
Type of Contract - |  | Flat Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate | Amount
1 | E- Building 1011, 1211 Conceal part fitting, Water proofing and Drainage line fitting work |  | 100% | 2 | Flats | 30000 | 60000
| Total Bill Amount | [5 empty] | 60000
| GST @ 18% | [5 empty] | 0
60000
Sixty Thousand Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 60000
TDS will be deducted as per applicable rules at your end
Approved By -

## 14
Payment Certificate
Company Name |  | SK. Salauddin |  |  | Invoice No. |  | 293
Vendor Name |  | Salauddin
To, Tanvi Infracon - Revanta Project |  |  |  |  | Date - | 2025-05-22
Type of Work - |  | Flat Plumbing work |  |  | Bill Date | 2025-05-18
Type of Contract - |  | Flat Plumbing work
Payment Details
Sr. No. | Items |  | % of Work Completed | Qty | Unit | Rate | Amount
B- Building
1 | C.P. Fitting work 7.5% (24 Flat X 2550) |  | 100% | 24 | Flats | 2550 | 61200
2 | Sanitary Fitting work 7.5% (24 Flat X 2550) |  | 100% | 24 | Flats | 2550 | 61200
3 | 200 mm Outer Road Rain water Line fitting work |  | 100% | 200 | R.ft. | 110 | 22000
4 | 300 X 300 Chamber for DG |  | 100% | 12 | Nos. | 1800 | 21600
5 | 600 X 2400 Chamber for SMC Water Line |  | 100% | 1 | Nos. | 6000 | 6000
6 | 900 X 1200 Chamber for Transformer Area |  | 100% | 1 | Nos. | 5000 | 5000
7 | B- Building 203 Flat Inlet Fitting, Internal Drainage and Water proofing work |  | 100% | 1 | Nos. | 30000 | 30000
| Total Bill Amount | [5 empty] | 207000
| GST @ 18% | [5 empty] | 0
207000
Two Lakh Seven Thousand Only
| Advance Payment | [5 empty] | 0
| Retention @ 5% to be deducted | [5 empty] | 0
| Balance Payment to be paid | [5 empty] | 207000
TDS will be deducted as per applicable rules at your end
Approved By -