## Plumbing
Amaya Corporation
10th Floor, 1001, Pramukh Orbit -2, Vesu Canal Road, Vesu, Surat
Email: contact@pramukh.co.in, Website: www.pramukh.co.in
WORK ORDER
Agency Name -S.K. Salauddin Plumber Person Name - Salaudin Address: At Priyanka City, Parvat Gam, Kumbhariya Gam, Surat- 395009 Phone Num - 9825573268 |  |  | Project Name - Pramukh Amaya, Surat Billing Address: 1001, Orbit-2, Vesu Canal Road, Vesu, Surat Contact Person: Mr. Bhavin - 8401469609
Quotation No.- 1, Dated - 7th Aug 2024 |  |  | GST No - 24ABZFA6800G1ZB
W.O. No.: AC/WO/24/03 |  |  | 2024-11-08
Subject - Plumbing Labour Work For Tower A, B and C Towers
Sr. No. | Work Description | Unit (Flats) | Rate (Rs.) | Amount ( In Rs.)
1 | Total Plumbing Work - Inlet Fitting, Internal Drainage Line, External Vertical Line upto First Basement Slab, Terrace Looping, Balcony Drain Line, AC Drain Line, UGT to OHWT Connection, C.P & Sanitary Fitting, Sunk Water Proofing (Toilet, Wash and Balcony Area) - 3 BHK Flats (C-D, G Tower) | 100 | 33500 | 3350000
2 | Total Plumbing Work - Inlet Fitting, Internal Drainage Line, External Vertical Line upto First Basement Slab, Terrace Looping, Balcony Drain Line, AC Drain Line, UGT to OHWT Connection, C.P & Sanitary Fitting, Sunk Water Proofing (Toilet, Wash and Balcony Area) - 2 BHK Flats (M Tower) | 52 | 25000 | 1300000
| Total |  |  | 4650000
| GST 18% |  | 0
Grand Total
| Amount in Words |  | Forty Six Lakhs Fifty Thousand Rupees Only
* | Terms & Conditions:
1 | Tax as applicable
2 | Payment Condition - Payment will be done in 15days after receipt of RA bill. RA shall be raised only for activity which is 100% Complete
3 | Payment Stages - Inlet Fitting Work - 20% Internal Drainage Line Work - 10% Water Proofing Work - 25% External Vertical Line Work - 20% Terrace Looping Work - 10% CP Fitting Work - 7.5% Sanitary Fitting Work - 7.5%
4 | All Bill Shall be approved by Site Engineer before submission to account dept.
5 | All work shall be done as per Standard Quality. If quality is found unsatisfactory, client reserves the right to give Debit for the same
6 | All work shall be done in Proper Line, Slope & Levels.
7 | All CP & Sanitary Fitting to be done at same level in all Toilets as specified in the drawings
8 | All Core Cut Finishing to be done by Plumbing Agency.
9 | All Work shall be done within agreed timeline, incase of delay, debit of 500/- Rs per day shall be charged
10 | It will be agency's responsibility to clean entire floor everyday once the work is completed
11 | Retention @ 5% will be kept in all RA bills
For, Amaya Developers |  | S.K. Salauddin

## Sheet1
[7 empty] | 3 BHK | 2 BHK
3 | A-B | Deepak | 48 | Salaudin | 100 | C-D, M | 48 | 52
3 | C-D | Salaudin | 48 | Deepak | 256 | A-B, I, J, K, L | 152 | 104
3 | E-F | Akrajul | 48 | Akrajul | 204 | E-F, G, O, P
3 | G | Akrajul | 52 | Naishad | 104 | H, N
3 | H | Naishad | 52 |  | 664
3 | I | Deepak | 52
3 | J | Deepak | 52
2 | K | Deepak | 52
2 | L | Deepak | 52
2 | M | Salaudin | 52
2 | N | Naishad | 52
2 | O | Akrajul | 52
2 | P | Akrajul | 52